## Read Me
Medical HRMS & Jameah — Task Tracker
Al-Riyada College for Health Sciences · status as of 21 Oct 2026
What this workbook is
One place to see what has been done on Medical HRMS (HR system) and Jameah (Ministry of Education data), what is being done now, and what is still pending.
It continues the 1 Oct 2026 tracker (HRM_TASK_TRACKER.md / .csv): tasks HR-01 to HR-32 keep their IDs and are updated; HR-33 onwards and JM-01 onwards are new.
Sheets
Summary | Counts by status, workstream and date. Updates by itself when you change a status in Tasks.
Tasks | Every task: when it was done, status, owner, evidence and the next step. Filter on any column.
Bugs | Every bug found during testing, its cause, the fix and how it was verified.
Decisions | Questions only the college, the Ministry or another team can answer. Yellow columns are for the answer.
Status values
Done | Built and tested.
Done – client UAT pending | Built and tested by the team; waiting for HR/client acceptance testing.
In progress | Being worked on.
Pending – decision needed | Waiting for an answer (see Decisions).
Pending – data / setup | Code is ready; needs data entry or server setup.
Pending – development | Not built yet.
Pending – other team | Needs the Education team, Finance or another party.
Planned | Agreed for later; not started.
How to update
Change the Status cell in Tasks (it has a drop-down). Add new tasks at the bottom with the next free ID. Summary and colours update automatically.
Sources
HRM_TASK_TRACKER.md/.csv, HRM_UAT_SCENARIOS.md, HRM_APPROVAL_MATRIX.md, JAMEAH_HRMS_* documents, MINISTRY_FIELD_MAPPING.html, Ministry schema V0.1, git history of medical_hrms (phpdevpro/edu-alriyada-hrm), test runs of 19–21 Oct 2026.
Companion files: Medical_HRMS_Jameah_Test_Cases.xlsx (for the testing team) and the Test Report.

## Summary
Summary
Counts are formulas over the Tasks and Bugs sheets. As of 21 Oct 2026.
Tasks by status | Tasks
Done
Done – client UAT pending
In progress
Pending – decision needed
Pending – data / setup
Pending – development
Pending – other team
Planned
Total tasks
Medical HRMS vs Jameah | Done (both Done statuses) | Open (everything else) | Total
Medical HRMS (HR-…)
Jameah (JM-…)
Work done by date | Tasks
Earlier (May – 5 Oct 2026)
19 Oct 2026
20 Oct 2026
21 Oct 2026
— (not done yet)
Workstream | Done | Done – client UAT pending | In progress | Pending – decision needed | Pending – data / setup | Pending – development | Pending – other team | Planned | Total
Foundation
Master data
Registration
Recruitment
HR dashboard
Self-service
Security
Leave
Approvals
Compliance
Integration
Payroll
Testing
Documentation
Academic presence
Employee master
Requests
Navigation
Infrastructure
Data
Deployment
Jameah
Bugs | Count
Fixed
Open
Open – other team
Open – check server

## Tasks
ID | Workstream | Task | When done | Status | Owner | Priority | Done so far / evidence | Next step / pending | Reference (commit / file)
HR-01 | Foundation | Custom Medical HRMS app and setup scripts | Earlier (May – 5 Oct 2026) | Done | Abdul Hakeem | Medium | App, setup scripts and migration hooks exist. Migration re-run several times on 19–21 Oct without errors or duplicates; Ministry fields, permissions and Jameah views are created on every migrate. | Run the same migration once on the production server. | hooks.py; patches.txt
HR-02 | Master data | Ministry lookup codes and validation | 19 Oct 2026 | Done | Abdul Hakeem | High | 9,867 Ministry codes loaded from the Arabic and Translated workbooks, every code with Arabic and English names (before: 8,330 showed the code as their name). Loaded automatically on migrate. Demo codes remapped and removed. | None. | 277442b; ministry_codes.py; data/ministry_codes.csv
HR-03 | Master data | Institute hierarchy and facility records | Earlier (May – 5 Oct 2026) | Pending – data / setup | HR | Medium | Branch, Agency, Deanery, College, Academic Department and Facility doctypes exist and are linked to Employee/Instructor. | HR to enter the real hierarchy and confirm employee placement. | create_institute_doctypes.py; create_facility_doctype.py
HR-04 | Registration | Job-level setup | Earlier (May – 5 Oct 2026) | In progress | Dinesh | Medium | Work started by Dinesh (commits 2–5 Oct). | Dinesh to confirm scope done and what remains. | HRM_TASK_TRACKER.md
HR-05 | Registration | Employee registration | 19 Oct 2026 | In progress | Dinesh / Abdul Hakeem | High | Ministry identity rules added (national ID 10 digits starting 1 for Saudis, Iqama 10 digits starting 2) and duplicates blocked (same identity number, home ID or job number). Mandatory Ministry fields enforced on save. | Dinesh to confirm remaining registration scope; complete EMP-00001 demo record (HR-53). | 1f88c78; ministry_lookup_validation.py
HR-06 | Recruitment | Job Applicant to Employee transfer | 19 Oct 2026 | Done – client UAT pending | Abdul Hakeem / Dinesh | High | Public application form -> Accept -> Create Employee tested in the browser on 19, 20 and 21 Oct. Creates Employee, login, Instructor / Academic Advisor / HOD records by role. Lost fields fixed on 20 Oct (HR-44). | HR to run one real hire on the test site. | job_application.py; 8390598
HR-07 | Registration | Qualifications, experience and Ministry profile fields | 20 Oct 2026 | Done | Abdul Hakeem | High | Jameah child tables (qualifications, academic experience, previous experience, training, awards, publications) on Employee. 'Appreciation' fixed to use the Ministry grade list on 20 Oct. These feed the Jameah Employee views. | None. | setup_employee_ministry_expected_fields.py; d690cb7
HR-08 | HR dashboard | HR dashboard and leave-management shortcuts | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem | High | Every dashboard link opens without an error (browser test HRD-03, 21 Oct). Counts fixed on 19 Oct. Academic Presence and Jameah sections added. | HR UAT. | page/hr_dashboard
HR-09 | Self-service | Employee self-service dashboard | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem | High | All 10 request types, leave request, details view and counters tested in the browser (ESS-01..17). | Employee UAT, including on a phone. | page/employee_dashboard
HR-10 | HR dashboard | Custom workspace styling | Earlier (May – 5 Oct 2026) | Done – client UAT pending | Abdul Hakeem | Low | Workspace renders (browser test HRD-04). | Check long labels and mobile layout during UAT. | public/css/workspace_theme.css
HR-11 | Self-service | Self-service in Instructor, HOD and other staff dashboards | — | Planned | Abdul Hakeem + Education team | High | Not started. Instructors with an Employee record can already use /app/employee-dashboard. | Add the request and leave cards to the Education dashboards (needs the Education team). | HRM_TASK_TRACKER.md
HR-12 | Security | HR roles, workspace visibility and login routing | 21 Oct 2026 | Done | Abdul Hakeem | High | HR Manager / HR User now land on the HR Dashboard after login, employees on the Employee Dashboard; users with an Education dashboard keep it (fix 21 Oct, browser-tested). | Deploy (HR-58). | 1ee80cd; login_redirect.py
HR-13 | Security | Own-record access and protected employee identity | 20 Oct 2026 | Done | Abdul Hakeem | High | 12 security tests pass (SEC-01..12): employees see only their own requests, records, licences and files; cannot approve, spoof or file HR-only requests. | None. | employee_permissions.py; self_service.py
HR-14 | Self-service | Customized employee request forms | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem | High | Each form's required fields, private attachment upload and sending tested in the browser. | HR UAT of the wording on each form. | self_service.py
HR-15 | Self-service | Request details and easier time selection | 20 Oct 2026 | Done | Abdul Hakeem | Medium | Hour/minute/AM-PM picker saves correct times (10:15–11:45 test); incomplete time refused; details dialog shows saved values. | None. | employee_dashboard.js
HR-16 | Self-service | Resume drafts and resubmit rejected requests | — | Pending – development | Abdul Hakeem | Medium | Drafts can be saved; employees cannot edit sent requests. | Let employees open their draft and send it; allow resubmitting a rejected request as a new one with history. | HRM_UAT_SCENARIOS.md #3
HR-17 | Self-service | Employee data correction: approval and apply to Employee | — | Pending – development | Abdul Hakeem + HR | Medium | Request form and HR status steps exist. | HR to confirm the steps; apply the approved change to the Employee record with an audit trail. | Employee Data Update Request
HR-18 | Leave | Editable leave types and policies on migrate | Earlier (May – 5 Oct 2026) | Done | Abdul Hakeem | Medium | Migration creates editable starter records and draft policies; 6 unit tests pass. | HR to confirm final policies. | setup_leave_defaults.py
HR-19 | Leave | Leave policy activation and allocations | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem + HR | High | Full leave flow tested in the browser: request -> approver approves and submits -> balance 21 -> 19. | Set real policies and allocations for real employees. | setup_local_leave_demo.py
HR-20 | Leave | Medical leave year and pay-stage controls | Earlier (May – 5 Oct 2026) | Done – client UAT pending | Abdul Hakeem + HR | High | 6 unit tests pass (stages, overlaps, caps). | HR to review stage rules; Finance to review payroll effect. | medical_leave.py
HR-21 | Leave | Monthly half-day and remote-work limits | Earlier (May – 5 Oct 2026) | Done – client UAT pending | Abdul Hakeem + HR | Medium | 6 unit tests pass. Remote-work limit is currently switched off in HR Settings. | HR to confirm limits and switch them on. | monthly_leave_policy.py
HR-22 | Leave | Employee balances and monthly usage display | 20 Oct 2026 | Done | Abdul Hakeem | Medium | Balance updates after approval (browser test APR-05). | None. | employee_dashboard.py
HR-23 | Leave | Carry-forward, service eligibility and holiday calendar | — | Pending – decision needed | HR | Medium | Demo weekend calendar only. | HR to give official holidays and carry-forward rules; set the Academic Holiday List in HR Settings. | HR Settings
HR-24 | Approvals | Manager, HR and Finance approval routing | 19 Oct 2026 | In progress | Abdul Hakeem + HR/Finance | High | Finance roles fixed on 19 Oct (Finance Manager or Accounts Manager accepted). HR approve/reject/issue tested. | Agree the approver per step with HR and Finance; build the workflow; label amounts in SAR (some messages say AED). | overrides/; HRM_APPROVAL_MATRIX.md
HR-25 | Approvals | Notifications, rejection reasons and audit trail | — | Pending – development | Abdul Hakeem + HR | Medium | Changes are tracked (track_changes). E-mail sending fails on this copy (HR-47). | Add rejection reason; send submit/approve/reject e-mails once the mail account works. | HRM_UAT_SCENARIOS.md
HR-26 | Compliance | Medical licences, contract renewal and separation | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem | Medium | Licence creation and own-licence visibility tested (LIC-01/02). Contract renewal is HR-only. | UAT of expiry reminders and separation. | Employee Medical License
HR-27 | Integration | Employee <-> Instructor link | 19 Oct 2026 | Pending – data / setup | HR | High | Linking tool and HR data sheet done (19 Oct). Only 1 of 216 instructors is linked to an Employee. | HR fills the Instructor data sheet, then run the import (HR-55). | link_existing_instructors.py; instructor_data_sheet.py
HR-28 | Integration | Automatic Employee/Instructor profile sync | — | Planned | HRM + Education teams | Low | Not started. | Agree which side owns each field, then build. | JAMEAH_HRMS_IMPLEMENTATION_PLAN.md
HR-29 | Payroll | Payroll inputs and approved-benefit handoff | — | Planned | HRM + Finance | Medium | Not started. | Define the handoff with Finance. | HRM and Finance Module Integration Roadmap.html
HR-30 | Payroll | Payroll calculations, accounting and reports | — | Planned | Finance + HRM | Medium | Not started. | Validate salary slips and partial-pay leave with Finance. | Roadmap
HR-31 | Testing | Automated and end-to-end testing | 21 Oct 2026 | Done | Abdul Hakeem | High | Browser end-to-end rounds on 19, 20 and 21 Oct (latest: see Test Report). 26 unit tests pass. Jameah views verified value by value. | Client UAT with the Test Cases workbook. | Test Report; Test Cases workbook
HR-32 | Documentation | Documentation and client sign-off | 21 Oct 2026 | In progress | Abdul Hakeem + HR | Medium | This tracker, the test cases workbook, the test report, Jameah README and VIEWS mapping. | HR / Finance sign-off after UAT. | docs/
HR-33 | Security | Job applications could grant admin roles | 19 Oct 2026 | Done | Abdul Hakeem | Critical | A guest could get System Manager through the public form. Fixed with an allow-list of hireable roles, checked again before conversion. | None. | 0ab539e
HR-34 | Recruitment | Each academic hire gets the records its dashboard needs | 19 Oct 2026 | Done | Abdul Hakeem | High | Instructor, Academic Advisor (+ Instructor) and Head of Department records created and linked; every hire gets the Employee role. | None. | 8390598
HR-35 | Recruitment | HR spreadsheet to complete Instructor Ministry data | 19 Oct 2026 | Done | Abdul Hakeem | High | Dated bilingual export/import sheet with checks and a colour-coded result file. | HR to fill it (HR-55). | 02f978e; instructor_data_sheet.py
HR-36 | Academic presence | Faculty schedules (HR requirement 1) | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem | High | Every teaching session per faculty member, room and mode; faculty filter; CSV export. Tested: 390 sessions, 58 faculty for 6–12 Sep 2026. | HR UAT. | 0578d3d; page/hr_academic_presence
HR-37 | Academic presence | Proctor schedules (HR requirement 2) | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem | High | Exam Committee proctor assignments by date, time and room. | Needs real exam committees in the system to show data. | 0578d3d
HR-38 | Academic presence | Students on campus per hour (HR requirement 3) | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem | High | Hourly expected / present / absent. Tested: 8 Sep 2026 = 858 expected, 397 present (matches attendance). | HR UAT. | 0578d3d
HR-39 | Academic presence | Faculty on campus after 4 PM (HR requirement 4) | 20 Oct 2026 | Done – client UAT pending | Abdul Hakeem | High | Daily list with evidence (device / class attendance / timetable); cut-off configurable in HR Settings. Tested: 27 people, 47 person-days in the test week. | Connect attendance devices for exact times (HR-56). | bfac883
HR-40 | Testing | Browser end-to-end test round 1 and fixes | 20 Oct 2026 | Done | Abdul Hakeem | High | 68 browser tests, 8 real bugs found and fixed (see Bugs sheet B-13..B-21). | None. | 7f0c5fc
HR-41 | Employee master | Saving an Employee who has a login failed | 20 Oct 2026 | Done | Abdul Hakeem | Critical | 'Could not find Gender: Gender::1' on every save of an employee with a login. Fixed in the Employee controller. | None. | 7f0c5fc; overrides/employee.py
HR-42 | Requests | Leave Return Request list failed for HR | 20 Oct 2026 | Done | Abdul Hakeem | High | Frappe rejects queries on a doctype named with ' from '. Renamed 'Return from Leave Request' -> 'Leave Return Request' (migration patch moves the data). | None. | 7f0c5fc; patches/rename_return_from_leave_request.py
HR-43 | Security | HR permissions on core doctypes | 20 Oct 2026 | Done | Abdul Hakeem | High | HR read access to Company, Instructor, Department Edu; select-only Role; Travel Request. Applied on migrate. | None. | hr_core_permissions.py
HR-44 | Recruitment | Applicant fields lost when converting to Employee | 20 Oct 2026 | Done | Abdul Hakeem | High | Work phone, extension, application category, expected salary, ID/passport and resume were dropped. Fields added to Employee. | None. | d690cb7
HR-45 | Security | HR users not taken to the HR Dashboard after login | 21 Oct 2026 | Done | Abdul Hakeem | High | Education's master branch has no HR roles in its landing list, so HR stayed on /app. Fixed from medical_hrms; browser-tested. | Deploy (HR-58). | 1ee80cd
HR-59 | Navigation | Employees saw a 'Medical HRMS' link that opened 'Not permitted' | 21 Oct 2026 | Done | Abdul Hakeem | High | Found by the 21 Oct error sweep: the top-bar breadcrumb on the Employee Dashboard and lists pointed employees to the HR-only workspace; one click showed 'Not permitted - No permission for Page'. Breadcrumbs now only point to workspaces the user can open (employees get 'Employee Self Service'). | Deploy (HR-58). Likely one source of the error the client reported. | workspace_access.py
HR-60 | Requests | HR got a 'No Read or Select Permission for Cost Center' pop-up on a new Expense Claim | 21 Oct 2026 | Done | Abdul Hakeem | High | Found by the 21 Oct error sweep: a new Expense Claim fills in the default cost center, which HR could not select. HR User and HR Manager now get select-only access to Cost Center and Project (as employees already have). Applied on migrate. | Deploy (HR-58). Likely one source of the error the client reported. | hr_core_permissions.py
HR-61 | Recruitment | Academic hire with a personal e-mail: Employee created but Instructor record silently missing | 21 Oct 2026 | Done | Abdul Hakeem | High | Education's master branch now requires Instructor e-mails ending in @alriyada.edu.sa. Converting an Instructor/Academic Advisor applicant with a personal e-mail created the Employee and then showed an orange 'Instructor record not created' warning. Now refused up front with 'College E-mail Needed' before anything is created; the Create Employee dialog says which address to use. | Deploy (HR-58). HR must enter the official college e-mail as Company Email for academic hires. | job_application.py; employee_job_applicant.js
HR-63 | Registration | Non-Saudi employees could not be saved: the form wiped their Iqama number | 21 Oct 2026 | Done | Abdul Hakeem | Critical | Found 21 Oct: the 19 Oct identity fix (HR-05, bug B-11) changed the server rule (Iqama mandatory for residents, home-country ID optional) but the Employee form script still had the old rule. Opening a non-Saudi employee hid and cleared the Iqama number and demanded the home-country ID, so HR could not save the record at all. Form now matches the Ministry rule; browser-tested with an Iqama holder. | Deploy (HR-58). Very likely one source of the error the client reported (any HR user opening a non-Saudi employee). | employee_ministry_lookup.js
HR-64 | Recruitment | Employees created from a job application opened as 'Not Saved' | 21 Oct 2026 | Done | Abdul Hakeem | High | The public form lets an applicant pick a special-needs type with 'Has special needs = No' and a Saudi enter a home-country ID. Those values were copied to the Employee; the form then cleared them on opening (record marked 'Not Saved', 'Leave site?' prompt) and the Ministry view would have sent a special-needs code for someone without special needs. The server now drops values that do not apply on every save; the views only send a special-needs type when the flag is set. | Deploy (HR-58). | ministry_lookup_validation.py; jameah/views.py
HR-65 | Recruitment | Create Employee dialog does not ask for Department and Work Location | — | Pending – development | Abdul Hakeem | Medium | Both are mandatory on the Employee form, so HR must fill them on the new employee before the record can be saved again ('Missing Fields'). Found 21 Oct. | Ask for both in the Create Employee dialog. | employee_job_applicant.js
HR-66 | HR dashboard | HR Portal and Employee Portal in the new college design | 21 Oct 2026 | Done | Abdul Hakeem | High | Same look as the Education team's new portals (Instructor Portal): left menu with sections, top bar with breadcrumb, EN/AR, dark mode, notifications and account menu, page heading, 'Today at a Glance' cards. Covers the HR Dashboard, Employee Dashboard, Academic Presence and Jameah Data Check; menu entries only show pages the user can open; phone layout; right-to-left Arabic with 216 new Arabic translations. Our own code and class names, so Education's changes cannot break these pages. | Client to review the look; standard Frappe lists and forms keep the normal desk. | hr_portal.js; hr_portal.css; translations/ar.csv
HR-62 | Security | HR User could not open the Holiday List ('Not permitted') | 21 Oct 2026 | Done | Abdul Hakeem | Medium | ERPNext grants Holiday List to HR Manager only, but HR Users manage employees (whose form links a holiday list) and check holidays when approving leave. HR User now has read-only access. | Deploy (HR-58). | hr_core_permissions.py
HR-46 | Testing | Full end-to-end test with error sweep (round 3) | 21 Oct 2026 | Done | Abdul Hakeem | High | All modules plus an error sweep of every page for four roles. Results in the Test Report. | Client UAT. | Test Report
HR-47 | Infrastructure | System e-mail account password cannot be decrypted | — | Pending – data / setup | Server admin | High | Error Log: 'Failed to decrypt key Email Account.Notifications.password' 10 times (13–20 Oct); 3 e-mails stuck. Every system e-mail fails while this is broken. | On the live server: open Email Account 'Notifications', re-enter the password, save, send a test e-mail. Check the Error Log there for the same error. | Error Log; Email Queue
HR-48 | Integration | Instructor form: linking an Employee fails on save | — | Pending – other team | Education team | Medium | Instructor copies gender/department from Employee into its own lists, which reject Ministry codes. Recruitment works around it. | Education team: remove or map those fetches on Instructor. | education Instructor doctype
HR-49 | Registration | Incomplete-employees report | — | Pending – development | Abdul Hakeem | Medium | Not started. | Report listing employees missing Ministry-mandatory fields. | —
HR-50 | Registration | Data sheet for non-academic staff | — | Pending – development | Abdul Hakeem | Medium | Instructor sheet exists (HR-35). | Same export/import for non-academic staff. | —
HR-51 | Recruitment | Duplicate fields on Employee Job Applicant | — | Pending – development | Abdul Hakeem / Dinesh | Low | Found during review. | Remove duplicated custom fields after checking data. | —
HR-52 | Registration | Identity number length: 9–10 digits (spec) vs exactly 10 (current check) | — | Pending – decision needed | HR + Ministry contact | Medium | Current rule: National ID and Iqama = exactly 10 digits (real format). Ministry document says civil registry 9–10 digits. | Confirm whether 9-digit numbers must be accepted. | ministry_lookup_validation.py
HR-53 | Data | Demo employee EMP-00001 misses mandatory Ministry fields | — | Pending – data / setup | HR | Low | It can't be saved again until completed. Belongs to the demo company 'Medical College'. | Complete or delete the demo record before go-live. | Employee EMP-00001
HR-54 | Data | Website logo file missing (/files/rchs-logo.png) | — | Pending – data / setup | Server admin | Low | Missing on the local copy; every page requests it. | Check the file exists on the live server. | Website Settings
HR-55 | Data | Link the 216 existing Instructors to Employees | — | Pending – data / setup | HR | High | Tool ready (HR-35). 1 of 216 linked. | HR fills the Instructor data sheet; run the import with commit. | instructor_data_sheet.py
HR-56 | Academic presence | Connect attendance devices | — | Pending – data / setup | HR + IT | Medium | Presence page already uses device check-ins when they exist (HRMS Employee Checkin). | Connect devices; map device user IDs to Employees. | bfac883
HR-57 | Academic presence | Set the Academic Holiday List | — | Pending – data / setup | HR | Medium | Not set; the page warns about it. | HR Settings -> Academic Holiday List; tick event types that suspend classes. | academic_presence_setup.py
HR-58 | Deployment | Deploy to the live server | — | Pending – data / setup | Abdul Hakeem + Server admin | High | Branches pushed: fix/hrm-e2e-approval-permission-bugs, feature/jameah-ministry-views (contains both). | Merge, pull on the server, bench migrate, restart; smoke-test with the Test Cases workbook. | GitHub phpdevpro/edu-alriyada-hrm
JM-01 | Jameah | Research: Jameah system, Ministry documents, view contract | 19 Oct 2026 | Done | Abdul Hakeem | High | Ministry schema V0.1, field mapping HTML, 'Views Data' PDF and code workbooks reviewed; findings shared. | None. | Jameah report
JM-02 | Jameah | Ministry views for Employees (5) and Students (10) | 20 Oct 2026 | Done | Abdul Hakeem | Critical | 15 views with the HTML column names; Ministry codes only; faculty excluded from Employee views; source records never changed. | Deploy (HR-58). | d690cb7; jameah/views.py; jameah/VIEWS.md
JM-03 | Jameah | Code crosswalk (Jameah Code Map) | 20 Oct 2026 | Done | Abdul Hakeem | High | 299 college values mapped to official codes by meaning; wrong codes in Education masters (City 90, REL001...) no longer reach the Ministry. | Review 3 values (JM-11). | jameah/code_map.py
JM-04 | Jameah | Jameah Settings | 20 Oct 2026 | Done | Abdul Hakeem | High | Institution values; P18, country 101 and GPA type pre-filled. | Fill 6 values (JM-10). | Jameah Settings
JM-05 | Jameah | Academic figures (GPA, credit hours) refreshed hourly | 20 Oct 2026 | Done | Abdul Hakeem | High | Follows the transcript; view answers in ~3 s instead of 30 s. | None. | jameah/summary.py
JM-06 | Jameah | Independent verification of every view | 20 Oct 2026 | Done | Abdul Hakeem | Critical | All 15 views match the source records value by value; 0 invalid codes. Re-run 21 Oct after the Education update (JM-18): all 15 OK. | Re-run after data changes: bench execute medical_hrms.jameah.verify.run | jameah/verify.py; test_jameah.py
JM-18 | Jameah | Ministry GPA and credit hours = the college's official figures | 21 Oct 2026 | Done | Abdul Hakeem | Critical | Found 21 Oct: Education's master branch now has one official GPA calculation (retakes, superseded fails, XF/W, legacy baselines) and one for credit hours. Our views still used the old rules: GPA differed from the transcript for 1,197 of 2,854 students and required hours for ~10%. The hourly summary now reads Education's official functions (read only, no change to Education); verified: GPA equals the transcript for 2,854 of 2,854 students; all 15 views OK. Refresh moved to the long queue (~7 min). | Deploy together with the Education master update (HR-58); re-run verify on the live server. | jameah/summary.py; jameah/verify.py
JM-07 | Jameah | Jameah Data Check page and Employee preview | 20 Oct 2026 | Done | Abdul Hakeem | High | HR sees gaps, invalid codes, settings to fill and source problems; 'Ministry (Jameah) Data' button on the Employee form. | None. | page/jameah_data_check
JM-08 | Jameah | Read-only database account for the Ministry agent | — | Pending – data / setup | Server admin | High | SQL generated by medical_hrms.jameah.views.grant_statements. | Create the account on the live server; give the Ministry host, port, database, user, password. | jameah/README.md
JM-09 | Jameah | Confirm view and column names with the Ministry | — | Pending – decision needed | Ministry contact (Ms. Najah) | Critical | Views use the HTML names; Ministry schema V0.1 names some columns differently (list in the Jameah report). | Ask which names the Jameah agent reads; renaming is a small change. | Jameah report
JM-10 | Jameah | Fill Jameah Settings (6 values) | — | Pending – decision needed | Academic Affairs | High | Empty values are sent as empty. | College code, campus city, study type (regular/bridging), program duration and unit. | /app/jameah-settings
JM-11 | Jameah | Map 3 college values to Ministry codes | — | Pending – decision needed | Academic Affairs | High | Program 'Bachelor of Science in Nursing' -> department; Major 'Sciences in Nursing'; status 'Internship' (238 students). | Pick the code in Jameah Code Map and set Verified. | /app/jameah-code-map
JM-12 | Jameah | Ministry fields with no source in the college system | — | Pending – decision needed | Academic Affairs + Education team | Medium | Scholarship, visa, warnings, rewards, clearance, thesis, evaluation grade, major type, language and relationship lists are sent empty. | Decide which to capture (Student Ministry Detail is filled for 1,256 of 3,357 students). | Jameah report
JM-13 | Jameah | Correct source data found by the checks | — | Pending – data / setup | Registrar / Education team | High | 1,067 graduates still 'Enrolled'; 1,378 students on plans with no total credits; 1,266 relative addresses in Sri Lanka; 240 placeholder birth dates; 39 graduates without a graduate document; 7 enrollments without date; 6 orphan rows. | Fix at the source; the Jameah Data Check page shows the counts. | /app/jameah-data-check
JM-14 | Jameah | Faculty views (8 sections) | — | Pending – development | Abdul Hakeem | High | Not started (this round covered Employees and Students). | Build and verify the same way. | MINISTRY_FIELD_MAPPING.html
JM-15 | Jameah | Institute views (20 sections) | — | Pending – development | Abdul Hakeem | Medium | Not started. | Build after Faculty; needs institute data from HR. | MINISTRY_FIELD_MAPPING.html
JM-16 | Jameah | Old Education viewJameah* views (42) | — | Pending – other team | Education team | Low | Left untouched; they send record names and NULLs in places. Ours are named jameah*. | Education team to retire them once ours are confirmed. | education/jameah_system
JM-17 | Jameah | Transcript GPA rounding at exact ties | 21 Oct 2026 | Done | Education team | Low | Resolved by Education's new GPA module (exact half-up rounding); the views now use it (JM-18). | None. | Jameah report

## Bugs
Bug ID | Found on | Area | Problem | Cause | Fix | Commit / task | Status | How verified
B-01 | 19 Oct 2026 | Travel Request | Every save crashed | Validation read fields that don't exist | Cost read from costings, checked on submit | 91b7697 | Fixed | E2E 19 Oct
B-02 | 19 Oct 2026 | Approvals | Finance approval impossible | Hooks accepted only Finance Manager, which had no access | Accept Finance Manager or Accounts Manager; grant access | 91b7697 | Fixed | E2E 19 Oct
B-03 | 19 Oct 2026 | Return from Leave | Employees could not send the request | Clearance guard compared against the wrong default | Compare with the Select's first option | 91b7697 | Fixed | E2E APR-06
B-04 | 19 Oct 2026 | Children Medical Allowance | Every claim blocked, even drafts | Unused Employee Grade requirement | Requirement removed | 91b7697 | Fixed | E2E ESS-12
B-05 | 19 Oct 2026 | Medical License | Employees could list everyone's licences | No own-record rule | Own-record permission rules | 91b7697 | Fixed | E2E LIC-02
B-06 | 19 Oct 2026 | HR Dashboard | Return-from-leave count always 0 | Doctype name casing | Corrected | 91b7697 | Fixed | E2E HRD-02
B-07 | 19 Oct 2026 | Employee Dashboard | Drafts counted as pending | Status filter | Drafts excluded | 91b7697 | Fixed | E2E ESS-15
B-08 | 19 Oct 2026 | Recruitment (security) | A guest could obtain System Manager via the public form | Role taken from the guest payload | Hireable-role allow-list, server-controlled fields protected | 0ab539e | Fixed | E2E REC-02
B-09 | 19 Oct 2026 | Recruitment | Academic hires landed on dashboards that couldn't find them | Only an Instructor record was created | Records per role (Advisor, HOD...) | 8390598 | Fixed | E2E REC-03/04
B-10 | 19 Oct 2026 | Ministry codes | 8,330 codes showed the code as their name; no Arabic | Importer read only the translated workbook | Merge Arabic + translated workbooks | 277442b | Fixed | Data check
B-11 | 19 Oct 2026 | Registration | Home-country ID required for non-Saudis instead of the Kingdom ID | Wrong rule | Ministry identity rules | 1f88c78 | Fixed | Unit + E2E EMP-05/06
B-12 | 20 Oct 2026 | Academic presence | Students on campus undercounted | Weekly timetable slots not expanded | Expand slots week by week within the term | 0578d3d | Fixed | 397 present matched attendance
B-13 | 20 Oct 2026 | Employee master | Saving any employee with a login failed (Gender::1) | ERPNext copies Ministry gender code to the User | Employee controller maps it to the core Gender | 7f0c5fc | Fixed | E2E EMP-01
B-14 | 20 Oct 2026 | Leave Return Request | HR list view and counts failed | Frappe rejects ' from ' in table names | Doctype renamed with a migration patch | 7f0c5fc | Fixed | E2E APR-07
B-15 | 20 Oct 2026 | Leave Control Panel | Error for HR without an Employee record | No Company read permission | HR read on Company | 7f0c5fc | Fixed | E2E HRD-03
B-16 | 20 Oct 2026 | HR Dashboard | Travel Request link refused for HR | HRMS grants System Manager only | HR permissions on Travel Request | 7f0c5fc | Fixed | E2E HRD-03
B-17 | 20 Oct 2026 | Academic presence | Faculty filter unusable for HR | No Instructor read for HR | Read-only Instructor access | 7f0c5fc | Fixed | E2E PRS-02
B-18 | 20 Oct 2026 | Recruitment | HR could not create Job Application Links | No select permission on Role | Select-only Role, filtered to hireable roles | 7f0c5fc | Fixed | E2E REC-03
B-19 | 20 Oct 2026 | Recruitment | Create Employee dialog refused the department | No Department Edu read for HR | Read-only Department Edu | 7f0c5fc | Fixed | E2E REC-03
B-20 | 20 Oct 2026 | Employee pages | Script error on every employee list/form page | Router not ready on first load | Null guard | 7f0c5fc | Fixed | Error sweep
B-21 | 20 Oct 2026 | Job application form | Extension accepted letters, failed after submit | Text input for a phone field | Phone input | 7f0c5fc | Fixed | E2E REC
B-22 | 20 Oct 2026 | Registration | 'Appreciation' offered GPA systems instead of grades | Wrong Ministry list in config | Student Evaluation Coding list | d690cb7 | Fixed | E2E REC-05
B-23 | 20 Oct 2026 | Recruitment | Work/home phone and application details lost on conversion | Fields missing on Employee | Fields added | d690cb7 | Fixed | E2E REC-06
B-24 | 21 Oct 2026 | Login | HR users not taken to the HR Dashboard | Education master has no HR roles in its landing list | medical_hrms boot_session hook | 1ee80cd | Fixed | E2E LGN-01/02
B-29 | 21 Oct 2026 | Requests | HR opening a new Expense Claim got 'You do not have Read or Select Permissions for Cost Center' | HR roles had no select permission on Cost Center / Project | Select-only Cost Center and Project for HR User and HR Manager | HR-60 | Fixed | Error sweep SWP-01/02
B-30 | 21 Oct 2026 | Recruitment | Academic hire with a personal e-mail: Employee created, Instructor record not created (orange warning) | Education master requires @alriyada.edu.sa for Instructors | Refuse up front with 'College E-mail Needed'; dialog hint | HR-61 | Fixed | E2E REC-03/04/08
B-31 | 21 Oct 2026 | Security | HR User: Holiday List opened 'Not permitted' | ERPNext grants Holiday List to HR Manager only | Read-only Holiday List for HR User | HR-62 | Fixed | Error sweep SWP-02
B-32 | 21 Oct 2026 | Registration | Non-Saudi employee: opening the form cleared the Iqama number and blocked saving | Form script kept the pre-19-Oct identity rule | Form follows the Ministry rule (Iqama mandatory, home-country ID optional) | HR-63 | Fixed | E2E EMP-08
B-33 | 21 Oct 2026 | Recruitment | Hired employees opened as 'Not Saved'; special-needs code could reach the Ministry with 'No special needs' | Values that do not apply copied from the application | Dropped on save; views guard the special-needs type | HR-64 | Fixed | E2E REC-09, REC-06
B-34 | 21 Oct 2026 | Jameah | Ministry GPA differed from the transcript for 1,197 students after the Education update | Views kept the old GPA / credit-hour rules | Use Education's official GPA and credit-hour functions | JM-18 | Fixed | verify.run: 15/15 OK
B-28 | 21 Oct 2026 | Navigation | Employees clicking the 'Medical HRMS' breadcrumb got 'Not permitted - No permission for Page' | Frappe chooses the breadcrumb workspace without a permission check | Keep only workspaces the user can open | HR-59 | Fixed | E2E NAV-01/02
B-25 | 21 Oct 2026 | E-mail | System e-mails fail: password cannot be decrypted | Email Account 'Notifications' password encrypted with another key | Re-enter the password on the server | HR-47 | Open | Error Log
B-26 | 21 Oct 2026 | Instructor (Education) | Linking an Employee in the Instructor form fails | fetch_from copies Ministry codes into Education lists | Education team to change the fetch | HR-48 | Open – other team | Reproduced 21 Oct
B-27 | 21 Oct 2026 | Website | Logo file missing (/files/rchs-logo.png) | File not on this copy | Check on the live server | HR-54 | Open – check server | Error sweep

## Decisions
ID | Decision needed | Who decides | Options / recommendation | Blocks tasks | Answer (fill in) | Answered on
DEC-01 | Which view and column names does the Jameah agent read: the HTML names or the Ministry schema V0.1 names? | Ministry contact (Ms. Najah) | Confirm with the Ministry; renaming is a small change. | JM-09, go-live of Jameah
DEC-02 | College code the Ministry assigned to RCHS (College Coding Guide) | Academic Affairs | From the Ministry licence; pick in Jameah Settings. | JM-10
DEC-03 | Study type for regular and for bridging students | Academic Affairs | List includes 0 Total regularity, 7 Bridging. | JM-10
DEC-04 | Program duration and unit | Academic Affairs | From the study plan. | JM-10
DEC-05 | Campus city (Study Location City) | Academic Affairs | Ministry city code, e.g. 0202000 Jeddah Governorate if applicable. | JM-10
DEC-06 | Ministry department and specialization for the nursing program | Academic Affairs | Candidates KL01 Nursing Sciences / KL03 Nursing. | JM-11
DEC-07 | Ministry status for 'Internship' students (238) | Academic Affairs | Most likely 0 'restricted (enrolled)'. | JM-11
DEC-08 | Accept 9-digit identity numbers? | HR + Ministry contact | Today exactly 10 digits for National ID / Iqama. | HR-52
DEC-09 | Approver for each request step and the currency label (SAR) | HR + Finance | Update HRM_APPROVAL_MATRIX.md. | HR-24
DEC-10 | Official holidays and carry-forward rules | HR | Needed for leave and presence. | HR-23, HR-57
DEC-11 | Ministry credit hours: Registered = hours registered this term; Passed = earned + bridged plan hours (so Passed + Remaining = Required, as on the student dashboard). The transcript also shows a lifetime 'registered' total and bridging calc-hours. | Academic Affairs | Recommended as built; confirm with the Ministry definitions. | JM-18